## 2 28 2024
Staff Meeting Minutes
Date: | 2024-02-28
Time: | 16:00
Topic: | Project Intiatin Meeting summary.
Attendees: | VAIBHAV,RUCHA,RAKSHIT,SAI
Absent:
Meeting Objective/s
Discuss and finalize the project plan. Assign roles and responsibilities to team members. Identify potential risks and develop a risk management plan
Agenda
Name |  | Topic | Time
VAIBHAV |  | Introduction and Project Overview-Discussion on project goals, scope, and deliverables | 17:30
RUCHA |  | Project Plan Presentation- Detailed discussion on the timeline, milestones, and deadlines | 17:30
SAI |  | Roles and Responsibilities Assignment- Assigning specific tasks and responsibilities to team members | 17:30
RAKSHIT |  | Risk Assessment and Management- Identification of potential risks and discussion on mitigation strategies | 17:30
Notes
The meeting began with an overview of the project's objectives by Vaibhav, emphasizing the importance of the project plan. Rucha presented the plan, discussing key milestones and deadlines.SAI was given the task of assigning roles and responsisbiltiies of each personfollowed by brief overview of risk assesessment by Rakshit.We documneted action itesm and agreed to meet for regual review of the work done. The meeting was concluded with an empahsis of effective communication and team work.
101Planners.com

## 3 5 2024
Staff Meeting Minutes
Date: | 2024-03-05
Time: | 4:00PM
Topic: | Definings roles and responsibility
Attendees: | VAIBHAV,RUCHA,RAKSHIT,SAI
Absent:
Meeting Objective/s
Define roles and responsibilities Discuss project plan components: timeline, milestones, deadlines, and risk management. Allocate tasks and establish communication channels
Agenda
Name |  | Topic | Time
VAIBHAV |  | Project Manager and Coordinator-Coordination and PlanningTeam Management Stakeholder Communication | 17:30
RUCHA |  | Content Creator and Educational Resource Specialist - Content Development Health Education Accessibility CollaborationUser Experience Enhancement Promotion of Health Literacy Compliance. | 17:30
SAI |  | Data Security and Compliance Officer -Regulatory Compliance Policy Development Risk Assessment Security Measures Implementation Training and Awareness Incident ResponseAudits and Monitorin | 17:30
RAKSHIT |  | Technical Lead and Developer -Technical Expertise,Software Architecture Design,Coding and Development. | 17:30
Notes
Each member's role was Clearly assigned- Vaibhav as Project Manager will look after coordination, planning, and stakeholder communication; Rakshith as Technical Lead will be responsible for software architecture, coding, and problem-solving; Rucha as Content Creator will handle educational resources, health literacy, and compliance; and Sai Deva as Data Security Officer will manage regulatory compliance and risk assessment. Clear deadlines were established to complete that task in timely manner. Different communication channel were agreed upon to establish effective information sharing.
101Planners.com

## 3 12 2024
Staff Meeting Minutes
Date: | 2024-03-12
Time: | 16:00
Topic: | Definings roles and responsibility
Attendees: | VAIBHAV,RUCHA,RAKSHIT,SAI
Absent:
Meeting Objective/s
Discuss and identify potential risks associated with the project. Assess the severity and likelihood of each risk. Develop mitigation strategies to address identified risks.
Agenda
Name |  | Topic | Time
VAIBHAV |  | Low user adoption-Likelyhood of customer not understaanding the product, due to employee resistance or unimpressive UI/UX | 17:30
RUCHA |  | Content Security- encryption of sensitive content, access controls, and regular content audits | 17:30
SAI |  | Data Breach and Non-compliance with Regulation | 17:30
RAKSHIT |  | System Downtime and Integration Failure | 17:30
Notes
During the meeting, various risks associated with the project were identified and assessed. These risks include the potential for a data breach, non-compliance with healthcare regulations, system downtime, ineffective user authentication, poor user adoption, and integration failure. Mitigation strategies were discussed for each risk, ranging from implementing security measures and conducting audits to establishing infrastructure and user training. The severity of each risk was evaluated, with measures in place to address them accordingly. Moving forward, continual monitoring and adaptation will be crucial to ensure the successful mitigation of these risks throughout the project's lifecycle
101Planners.com

## 4 20 2024
Staff Meeting Minutes
Date: | 2024-03-12
Time: | 16:00
Topic: | Definings roles and responsibility
Attendees: | VAIBHAV,RUCHA,RAKSHIT,SAI
Absent:
Meeting Objective/s
Discuss and identify document creation, lesson learnt and design interface with the project.
Agenda
Name |  | Topic | Time
VAIBHAV |  | Meetings Minutes add on | 17:30
RUCHA |  | Design Interface | 17:30
SAI |  | Lessons Learned | 17:30
RAKSHIT |  | Testing | 17:30
Notes
During the meeting, various risks associated with the project were identified and assessed. These risks include the potential for a data breach, non-compliance with healthcare regulations, system downtime, ineffective user authentication, poor user adoption, and integration failure. Mitigation strategies were discussed for each risk, ranging from implementing security measures and conducting audits to establishing infrastructure and user training. The severity of each risk was evaluated, with measures in place to address them accordingly. Moving forward, continual monitoring and adaptation will be crucial to ensure the successful mitigation of these risks throughout the project's lifecycle
101Planners.com